## PMR 1st sem 2023
ANNEX B |  | ANNEX A
MARITIME INDUSTRY AUTHORITY RO XII Procurement Monitoring Report as of June 30, 2023 |  | Department of Budget and Management Annual Procurement Plan for FY 2006
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| Fuel Consumptions for Service Vehicles - Honda Mobilio SAB 5510 & Mits Adventure SFU 743 - Jan.-May 2023 | [19 empty] | MRO XII | NO | Direct Contracting | [9 empty] | 2023-01-03 |  | 2023-06-30 | 2023-06-30 | GoP | 120000 | 120000 |  | 104413.22 | 104413.22
| Snacks & Supplies Expenses for the 1st & 2nd Qtr Multi-Sectoral Advisory Board (MSAB) Meeting | [19 empty] | MRO XII | NO | Shopping | [9 empty] | 2023-03-27 |  | 2023-03-28 | 2023-03-28 | GoP | 30000 | 30000 |  | 7796 | 7796
| Risograph services of various Office Application Forms - Jan.-June 2023 | [19 empty] | MRO XII | NO | NP-53.9 - Small Value Procurement | [9 empty] | 2023-04-27 |  | 2023-05-25 | 2023-05-25 | GoP | 15000 | 15000 |  | 9362 | 9362
| Common Office/Janitorial/Utility Supplies for 2nd Quarter | [19 empty] | MRO XII | NO | NP-53.9 - Small Value Procurement | [9 empty] | 2023-04-27 |  | 2023-05-26 | 2023-05-26 | GoP | 430000 | 430000 |  | 39213.5 | 39213.5
| Repair & Maintenance for Honda Mobilio SAB 5510 for Jan.2023-June 2023 | [19 empty] | MRO XII | NO | NP-53.9 - Small Value Procurement | [9 empty] | 2023-04-24 |  | 2023-04-25 | 2023-04-25 | GoP | 50000 | 50000 |  | 14400 | 14400
| Meals/Snacks/Supplies Expenses for the 49th MARINA Anniversary Celebration on June 01, 2023, Conduct of GAD/GST Assessment for Stakeholders (Mid-Year)/ PGS-SPMS | [19 empty] | MRO XII | NO | NP-53.9 - Small Value Procurement | [9 empty] | 2023-05-29 |  | 2023-06-01 | 2023-06-01 | GoP | 70000 | 70000 |  | 32894.72 | 32894.72
| Venue, Foods, Accomodation & Supplies Expenses for Office's Mid-Year 2023 Performance Assessment and Planning | [19 empty] | MRO XII | NO | NP-53.9 - Small Value Procurement | [9 empty] | 2023-06-20 |  | 6/23-24/2023 | 2023-06-24 | GoP | 85000 | 85000 |  | 73400.2 | 73400.2
| Meals & Supplies Expenses for Seafarer's Day Celebration | [19 empty] | MRO XII | NO | NP-53.9 - Small Value Procurement | [9 empty] | 2023-06-23 |  | 2023-06-26 | 2023-06-26 | GoP | 40000 | 40000 |  | 21593.5 | 21593.5
| Cash Bond of one (1) Accountable Staff for Supplies | [19 empty] | MRO XII | NO | NP-53.5 Agency-to-Agency | [9 empty] | 2023-04-18 |  | 2023-04-20 | 2023-04-20 | GoP | 15000 | 15000 |  | 3525 | 3525
| Rental of Office Building for the month of January to June 2023 | [19 empty] | MRO XII | NO | Direct Contracting | [9 empty] | 2023-01-03 |  | 2023-06-30 | 2023-06-30 | GoP | 730000 | 730000 |  | 354816 | 354816
| Monthly Security Services - Jan.-June 2023 | [19 empty] | MRO XII | NO | Direct Contracting | [9 empty] | 2023-01-03 |  | 2023-06-30 | 2023-06-30 | GoP | 40320 | 40320 |  | 20160 | 20160
| Cable Subscriptions - Jan-June 2023 | [19 empty] | MRO XII | NO | Direct Contracting | [9 empty] | 2023-01-03 |  | 2023-06-30 | 2023-06-30 | GoP | 6000 | 6000 |  | 3000 | 3000
| Communication Expenses (landlines/internet & postpaid) January to June 2023 | [19 empty] | MRO XII | NO | Direct Contracting | [9 empty] | 2023-01-03 |  | 2023-06-30 | 2023-06-30 | GoP | 199104 | 199104 |  | 108436.56 | 108436.56
| Expenses for Women's Month - Tarpaulin only | [19 empty] | MRO XII | NO | Shopping | [11 empty] | 2023-03-01 | 2023-03-01 | GoP | 40000 | 40000 |  | 810 | 810
| Expenses for COA Entrance/Exit Conference 1st Sem | [19 empty] | MRO XII | NO | Shopping | [11 empty] | 2023-06-07 | 2023-06-07 | GoP | 3000 | 3000 |  | 1831 | 1831
| Repair & Maintenance of Split Type Aircondition Units (2 units) | [19 empty] | MRO XII | NO | Direct Contracting | [9 empty] | 2023-06-29 |  | 2023-06-29 | 2023-07-06 | GoP | 9000 | 9000 |  | 14500 | 14500
| Plumbing works of CR with accessories (1) | [19 empty] | MRO XII | NO | Direct Contracting | [11 empty] | 2023-04-03 | 2023-04-03 | GoP | 15000 | 15000 |  | 444.25 | 444.25
| Communication Expenses (postage/courier) - Jan.-June 2023 | [19 empty] | MRO XII | NO | Direct Contracting | [11 empty] | 2023-06-30 | 2023-06-30 | GoP | 20500 | 20500 |  | 14818 | 14818
| Utility Expenses: Electricity & Water Consumptions - Jan. - June 2023 | [19 empty] | MRO XII | NO | Direct Contracting | [11 empty] | 2023-06-30 | 2023-06-30 | GoP | 52000 | 52000 |  | 217353.85 | 217353.85 | [8 empty] | due to increase of usage and rates
| Potable Water Consumptions (Drinking Water Refill) - Jan. - June 2023 | [19 empty] | MRO XII | NO | Direct Contracting | [11 empty] | 2023-06-30 | 2023-06-30 | GoP | 21000 | 21000 |  | 4175 | 4175
| Photocopies of MRO12 Documents - Jan-June 2023 | [19 empty] | MRO XII | NO | Direct Contracting | [11 empty] | 2023-06-30 | 2023-06-30 | GoP | 20000 | 20000 |  | 17800 | 17800
| Zoom Account Subscription | [19 empty] | MRO XII | NO | Shopping | [11 empty] | 4/10/2023 | 4/10/2023 | GoP | 9000 | 9000 |  | 847.25 | 847.25
[38 empty] | 0 |  |  | 0
Total Alloted Budget of Procurement Activities | [37 empty] | 2019924
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 1065590.05
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 954333.95
0N-GOING PROCUREMENT ACTIVITIES
0
0
0
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 0
[21 empty] | Prepared by: | [7 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | CECILIA G. JARABELO, AO IV | [7 empty] | CECILIA G. JARABELO, AO IV | [10 empty] | FARIDA B. GUARIÑO, OIC-Regional Director
[21 empty] | BAC Secretariat | [7 empty] | BAC Chairperson | [10 empty] | Head of the Procuring Entity

## Sheet1
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement